JNC Network / JS Communication — Integrated CRM Platform

Master Architecture & Implementation Plan

Prepared for: JNC Network / JS Communication Scope: Lead management, WhatsApp automation, IndiaMART integration, order & shipment lifecycle, electronic components inventory & warehousing, RBAC, reporting, and a vibrant animated UI.

Working assumptions (stated explicitly since they weren't specified — adjust and I'll re-cut estimates):

- Team size: 5–30 concurrent users (owner/boss, 2–4 admins, several sales/employee seats), growing to ~50 over 2 years.

- 1–3 warehouses/godowns to start, India-based, single currency (INR), GST-aware invoicing later.

- WhatsApp via an official BSP (Business Solution Provider) — e.g. Interakt, WATI, Gupshup, AiSensy — rather than raw Meta Cloud API integration, for faster go-live and built-in template management. (Raw Cloud API is a fallback covered in the tech stack section.)

- IndiaMART integration uses their Lead Manager (CRM) Push API / Pull API, which delivers leads as they're captured — no scraping.

- Budget target: lean but professional — self-hosted or single-cloud-region deployment, not enterprise-scale infra.

1. Executive Summary

This plan delivers a single system of record — call it JNC-CRM — that replaces spreadsheets and scattered WhatsApp threads with one pipeline: lead capture → qualification → follow-up automation → quotation → order → dispatch → delivery → repeat business, backed by a real inventory ledger for electronic components across warehouses, and role-based dashboards that are visual and fast to scan on a factory-floor or sales-desk phone.

It is built in 5 phases over ~20 weeks by a small team (see Section 14), with inventory and WhatsApp automation prioritized early since they compound in value the sooner they're live.

2. System Architecture Overview

flowchart TB

subgraph Sources["Lead Sources"]

IM[IndiaMART Lead API]

WEB[Website Contact Forms]

MAN[Manual Entry / CSV Import]

WA_IN[Inbound WhatsApp Messages]

end

subgraph Core["JNC-CRM Core Platform"]

API[REST API Gateway / Auth]

LEADSVC[Lead Service]

CONTACTSVC[Contact & Company Service]

ORDERSVC[Order & Quotation Service]

INVSVC[Inventory & Warehouse Service]

SHIPSVC[Shipment Service]

AUTOMATION[Automation & Rules Engine]

REPORT[Reporting & KPI Service]

AUDIT[Audit & Logging Service]

NOTIF[Notification Dispatcher]

end

subgraph Integrations["External Integrations"]

WABA[WhatsApp Business API / BSP]

EMAIL[Email - SMTP / SendGrid]

VOIP[Telephony / VoIP - optional]

SMS[SMS Gateway - optional]

end

subgraph Data["Data Layer"]

PG[(PostgreSQL - primary)]

REDIS[(Redis - queues/cache)]

S3[(Object Storage - files/images)]

ES[(Search Index - optional, leads/products)]

end

subgraph Clients["Client Apps"]

WEBAPP[Web App - React]

MOBILE[Mobile App - React Native / PWA]

end

IM --> API

WEB --> API

MAN --> API

WA_IN --> WABA --> API

API --> LEADSVC

API --> CONTACTSVC

API --> ORDERSVC

API --> INVSVC

API --> SHIPSVC

API --> REPORT

LEADSVC --> AUTOMATION

ORDERSVC --> AUTOMATION

AUTOMATION --> NOTIF

NOTIF --> WABA

NOTIF --> EMAIL

NOTIF --> SMS

LEADSVC --> PG

CONTACTSVC --> PG

ORDERSVC --> PG

INVSVC --> PG

SHIPSVC --> PG

AUTOMATION --> REDIS

REPORT --> PG

LEADSVC --> AUDIT

ORDERSVC --> AUDIT

INVSVC --> AUDIT

API --> S3

API --> ES

WEBAPP --> API

MOBILE --> API

Pattern: modular monolith at launch (single deployable, cleanly separated service modules) → split into microservices later only if a specific module (e.g. inventory, automation) needs independent scaling. This avoids premature distributed-systems overhead for a 5–30 user system while keeping a clean seam to split later.

3. Data Model

3.1 Entity-Relationship Diagram

erDiagram

COMPANY ||--o{ CONTACT : has

COMPANY ||--o{ LEAD : "source of"

CONTACT ||--o{ LEAD : "associated with"

USER ||--o{ LEAD : "owns/assigned"

LEAD ||--o{ LEAD_ACTIVITY : has

LEAD ||--o{ QUOTATION : generates

LEAD ||--o{ FOLLOWUP_SEQUENCE_RUN : triggers

QUOTATION ||--o{ QUOTATION_LINE : contains

QUOTATION ||--|| ORDER : "converts to"

ORDER ||--o{ ORDER_LINE : contains

ORDER ||--o{ SHIPMENT : fulfilled_by

ORDER ||--o{ STATUS_HISTORY : tracked_by

PRODUCT ||--o{ SKU : has

SKU ||--o{ STOCK_ITEM : "stocked as"

SKU ||--o{ ORDER_LINE : "ordered as"

SKU ||--o{ QUOTATION_LINE : "quoted as"

WAREHOUSE ||--o{ LOCATION_BIN : contains

LOCATION_BIN ||--o{ STOCK_ITEM : holds

STOCK_ITEM ||--o{ STOCK_MOVEMENT : "changed by"

STOCK_ITEM ||--o{ BATCH_LOT : "tracked as"

SHIPMENT ||--o{ SHIPMENT_LINE : contains

SHIPMENT_LINE }o--|| STOCK_ITEM : "drawn from"

SHIPMENT ||--o{ STATUS_HISTORY : tracked_by

USER ||--o{ AUDIT_LOG : performs

USER }o--|| ROLE : "has"

ROLE ||--o{ PERMISSION : grants

MESSAGE_TEMPLATE ||--o{ MESSAGE_LOG : "used in"

LEAD ||--o{ MESSAGE_LOG : "receives"

AUTOMATION_RULE ||--o{ MESSAGE_LOG : triggers

LEAD {

uuid id PK

string source "indiamart|web|manual|whatsapp"

string status "new|contacted|qualified|quoted|won|lost"

uuid company_id FK

uuid contact_id FK

uuid assigned_to FK

string product_interest

string city

decimal estimated_value

timestamp captured_at

timestamp last_contacted_at

string lost_reason

}

PRODUCT {

uuid id PK

string name

string category "resistor|capacitor|ic|pcb|connector|module|misc"

string manufacturer

string datasheet_url

}

SKU {

uuid id PK

uuid product_id FK

string sku_code

string package_type

decimal unit_price

decimal cost_price

int reorder_point

int reorder_qty

}

STOCK_ITEM {

uuid id PK

uuid sku_id FK

uuid warehouse_id FK

uuid bin_id FK

int quantity_on_hand

int quantity_reserved

string batch_no

date expiry_or_mfg_date

}

STOCK_MOVEMENT {

uuid id PK

uuid stock_item_id FK

string movement_type "inward|outward|transfer|adjustment|return"

int quantity

uuid performed_by FK

string reference_doc

timestamp moved_at

}

ORDER {

uuid id PK

uuid lead_id FK

uuid company_id FK

string status "draft|confirmed|processing|dispatched|delivered|completed|cancelled"

decimal total_value

timestamp order_date

string payment_status

}

SHIPMENT {

uuid id PK

uuid order_id FK

string carrier

string tracking_number

string status "pending|packed|dispatched|in_transit|delivered|failed"

uuid dispatched_from_warehouse FK

timestamp dispatched_at

timestamp delivered_at

}

USER {

uuid id PK

string employee_code

string name

string phone

string email

uuid role_id FK

boolean active

timestamp created_at

uuid created_by FK

}

ROLE {

uuid id PK

string name "super_admin|admin|sub_admin|employee"

}

AUTOMATION_RULE {

uuid id PK

string trigger_event

string condition_json

string action_type "send_whatsapp|send_email|assign_lead|create_task"

uuid template_id FK

boolean active

}

3.2 Key Entity Notes

- Batch/Lot tracking lives on STOCK_ITEM + BATCH_LOT so components with date codes or reels can be traced to the exact inward shipment — critical for electronic components where suppliers/date codes matter for warranty/RMA.

- STATUS_HISTORY is a generic append-only table (entity_type, entity_id, from_status, to_status, changed_by, changed_at, note) reused by both ORDER and SHIPMENT — this is your audit trail for lifecycle stages, separate from the general AUDIT_LOG (which covers logins, permission changes, record edits/deletes).

- Soft-delete everywhere: deleted_at nullable column on all core tables. Nothing is hard-deleted; sub-admins/employees never get physical delete rights (see RBAC).

4. Core Workflows (Sequence Flows)

4.1 Lead Capture → Qualification → Follow-up

sequenceDiagram

participant IM as IndiaMART API

participant SYS as JNC-CRM

participant RULE as Automation Engine

participant WA as WhatsApp BSP

participant EMP as Sales Employee

IM->>SYS: New lead webhook/pull (buyer, product, city, phone)

SYS->>SYS: De-dupe (phone+product), create LEAD (status=new)

SYS->>RULE: Evaluate "lead.created" rules

RULE->>WA: Send instant WhatsApp template ("Thanks for inquiry...")

RULE->>SYS: Auto-assign to employee (round-robin / territory)

SYS-->>EMP: Push notification "New lead assigned"

EMP->>SYS: Marks lead "contacted" after call/chat

SYS->>RULE: Evaluate "no response in 24h" rule (scheduled)

RULE->>WA: Send follow-up template #1

Note over RULE: Sequence continues per configured cadence<br/>(Day 0, Day 1, Day 3, Day 7) until reply or opt-out

EMP->>SYS: Marks lead "qualified"

SYS-->>EMP: Prompt to create Quotation

4.2 Quotation → Order → Dispatch → Delivery

sequenceDiagram

participant EMP as Sales Employee

participant SYS as JNC-CRM

participant INV as Inventory Service

participant WH as Warehouse Staff

participant WA as WhatsApp BSP

participant CUST as Customer

EMP->>SYS: Create Quotation (SKUs, qty, price) from Lead

SYS->>WA: Send quotation PDF link via WhatsApp

CUST->>SYS: Approves (reply / portal click / employee marks approved)

SYS->>SYS: Convert Quotation → Order (status=confirmed)

SYS->>INV: Reserve stock (quantity_reserved += qty)

alt Stock insufficient

INV-->>SYS: Shortfall flag

SYS-->>EMP: Alert: raise Purchase/Reorder

else Stock sufficient

SYS-->>WH: Task: Pick & Pack

WH->>SYS: Confirms picked (STOCK_MOVEMENT: outward)

WH->>SYS: Marks Shipment "packed" → "dispatched"

SYS->>WA: Auto-send dispatch notification + tracking

SYS->>SYS: Order status → dispatched

CUST-->>SYS: Delivery confirmation (carrier webhook / manual)

SYS->>WA: Auto-send delivery confirmation + feedback request

SYS->>SYS: Order status → delivered → completed

end

4.3 Inventory Reorder Cycle

sequenceDiagram

participant CRON as Scheduled Job

participant INV as Inventory Service

participant ADMIN as Admin

participant SUP as Supplier (via WhatsApp/Email)

CRON->>INV: Nightly check: quantity_on_hand < reorder_point

INV->>ADMIN: Low-stock alert (dashboard + WhatsApp/email digest)

ADMIN->>SUP: Raise PO (manual or semi-auto template)

SUP-->>ADMIN: Confirms / ships

ADMIN->>INV: Record Inward (STOCK_MOVEMENT: inward, batch_no, qty)

INV->>INV: Update quantity_on_hand, log movement

5. Roles & Permissions (RBAC)

| Capability | Super-Admin (Boss) | Admin | Sub-Admin | Employee |
| --- | --- | --- | --- | --- |
| Create/deactivate users, assign IDs | ✅ | ✅ (own team only) | ❌ | ❌ |
| Reset credentials | ✅ (anyone) | ✅ (own team) | ❌ | ✅ (self only) |
| View all leads (org-wide) | ✅ | ✅ | 🔶 (assigned region/team) | 🔶 (assigned only) |
| Edit/reassign any lead | ✅ | ✅ | 🔶 (own team's) | ❌ (own only) |
| Delete records (soft-delete) | ✅ | ✅ | ❌ | ❌ |
| Configure automation rules/templates | ✅ | ✅ | 🔶 (view only) | ❌ |
| Approve quotations above threshold | ✅ | ✅ | 🔶 (below threshold) | ❌ |
| Warehouse stock adjustments | ✅ | ✅ | ✅ (own warehouse) | ❌ (view only) |
| View financial/cost data (cost price, margins) | ✅ | ✅ | ❌ | ❌ |
| View reports (org-wide) | ✅ | ✅ | 🔶 (team-scoped) | 🔶 (self-scoped) |
| Export data (CSV) | ✅ | ✅ | 🔶 (limited) | ❌ |
| Audit log access | ✅ | 🔶 (own team's actions) | ❌ | ❌ |

Implementation pattern: permissions stored as role → permission[] plus row-level scoping via assigned_to / warehouse_id / team_id filters injected at the query layer (not just UI hiding). Every API endpoint checks both role permission and row-level scope server-side — never trust client-side hiding alone.

Credential/ID assignment flow: Admin creates user → system generates employee_code (e.g. JNC-EMP-0042) + temp password → forced password reset on first login → optional 2FA via WhatsApp OTP.

6. Integrations

6.1 IndiaMART

- Use IndiaMART's CRM/Lead Manager API (push-based webhook if available on your plan, else scheduled pull every 5–10 min via their Lead API with START_TIME/END_TIME params).

- Map fields: SENDER_NAME, SENDER_MOBILE, SENDER_EMAIL, SUBJECT, QUERY_MESSAGE, SENDER_CITY, PRODUCT → LEAD entity, with source=indiamart and raw payload archived in lead_raw_payload (JSONB) for traceability/debugging.

- De-duplication key: normalized phone number + product category within a rolling 30-day window (configurable) to avoid duplicate leads from repeat inquiries — flag as "repeat inquiry" on existing lead instead of creating a new one.

6.2 WhatsApp Business API

- Recommended: BSP-mediated (Interakt / WATI / Gupshup / AiSensy) for template approval workflow, built-in inbox, and faster setup — typically live in 1–2 weeks including Meta business verification.

- Template categories to pre-build: lead acknowledgment, follow-up 1/2/3, quotation sent, order confirmed, dispatch notification (with tracking), delivery confirmation, payment reminder, feedback/NPS request, reorder/win-back campaign.

- All outbound automated messages must use pre-approved Meta templates (24-hour session window rule applies for free-form replies after customer-initiated contact).

- Two-way sync: inbound WhatsApp replies create/update MESSAGE_LOG and can trigger automation (e.g., "if customer replies 'yes'" → mark lead qualified).

6.3 Email & Telephony

- Transactional email (quotation PDFs, invoices, reports) via SMTP relay or SendGrid/Amazon SES.

- Optional VoIP/telephony (Exotel, Knowlarity, or similar India-based click-to-call providers) — logs call attempts as LEAD_ACTIVITY with recording link, click-to-call button from the lead card.

6.4 CSV Import

- Generic importer with column-mapping UI (map arbitrary CSV headers → CRM fields), validation preview before commit, and de-dupe check against existing contacts/leads by phone/email.

7. API Specification (Representative Endpoints)

Base: /api/v1 · Auth: JWT bearer + refresh token · All list endpoints support ?page&limit&sort&filter[field]=value.

| Method | Endpoint | Purpose | Role Gate |
| --- | --- | --- | --- |
| POST | /auth/login | Login (employee_code/email + password) | Public |
| POST | /auth/reset-password | Self-service reset (OTP via WhatsApp) | Authenticated |
| POST | /users | Create user + auto-generate ID | Admin+ |
| PATCH | /users/{id}/deactivate | Deactivate user | Admin+ |
| GET | /leads | List leads (filterable by status/source/assignee) | Scoped |
| POST | /leads | Manual lead creation | Employee+ |
| POST | /webhooks/indiamart | Inbound IndiaMART lead push | System (signed) |
| PATCH | /leads/{id}/status | Update lead status | Scoped |
| POST | /leads/{id}/activities | Log call/note/meeting | Scoped |
| POST | /leads/import | CSV import | Sub-admin+ |
| POST | /quotations | Create quotation from lead | Employee+ |
| POST | /quotations/{id}/convert-to-order | Convert on approval | Employee+ |
| GET | /orders | List orders (status filter) | Scoped |
| PATCH | /orders/{id}/status | Update order lifecycle status | Scoped |
| GET | /inventory/stock | Stock levels by SKU/warehouse | Scoped |
| POST | /inventory/movements | Record inward/outward/adjustment | Sub-admin+ |
| POST | /inventory/transfers | Warehouse-to-warehouse transfer | Sub-admin+ |
| GET | /inventory/reorder-alerts | SKUs below reorder point | Admin+ |
| POST | /shipments | Create shipment for order | Sub-admin+ |
| PATCH | /shipments/{id}/status | Update dispatch/delivery status | Sub-admin+ |
| POST | /webhooks/whatsapp | Inbound WhatsApp message/status | System (signed) |
| POST | /automation-rules | Create/edit rule | Admin+ |
| GET | /reports/lead-conversion | Funnel metrics | Scoped |
| GET | /reports/stock-aging | Aging inventory report | Admin+ |
| GET | /audit-logs | Audit trail | Super-admin/Admin |

Pattern notes: idempotency keys on all POST writes triggered by webhooks (IndiaMART/WhatsApp can redeliver); optimistic locking (version column) on ORDER/STOCK_ITEM to prevent race conditions on concurrent stock reservation.

8. Inventory & Warehouse Management

- Warehouse → Bin/Location hierarchy: Warehouse (e.g. "Bengaluru Main") → Zone → Rack → Bin (e.g. BLR-A-03-B12), so any SKU can be located physically in seconds — important for small electronic components (resistors, ICs) where visual search is impractical.

- Reorder logic: per-SKU reorder_point and reorder_qty, computed alerts run nightly; optionally auto-generate a draft Purchase Order for admin approval rather than fully automated purchasing (keeps a human in the loop for supplier negotiation).

- Batch/Lot & date-code tracking: every inward movement recorded against a batch_no; outward movements default to FIFO (First-In-First-Out) by batch, overridable manually — critical for components with limited shelf life (electrolytic capacitors, MOSFETs with date-sensitive specs) or where customers require date-code traceability for RMA.

- Stock reservation: confirming an order reserves stock (quantity_reserved) without decrementing quantity_on_hand until actual pick/pack — prevents overselling while keeping visibility of "available to promise" = on_hand - reserved.

- Transfer workflow: inter-warehouse transfer creates paired STOCK_MOVEMENT records (outward at source, inward at destination) with an in-transit intermediate state, so stock isn't "lost" mid-transfer in reports.

- Cycle counts: scheduled/manual stock-count sessions that reconcile system quantity vs physical count, logging variance as an adjustment movement with mandatory reason code.

9. UI/UX & Visual Design System

9.1 Design Direction

A vibrant, high-contrast, motion-forward dashboard suited to a fast-moving sales+ops floor — think confident color-blocking per module (not muted enterprise gray), large legible numbers, and micro-animations that make status changes feel alive without being distracting.

9.2 Color System (module-coded)

| Module | Primary | Accent | Use |
| --- | --- | --- | --- |
| Leads / Pipeline | Electric Blue #2E5EFF | Sky #8FB8FF | Lead cards, funnel stages |
| WhatsApp / Messaging | WhatsApp Green #25D366 | Mint #B9F5D0 | Message threads, automation badges |
| Orders / Quotations | Amber #FFB020 | Cream #FFE8B8 | Order stage chips, quote status |
| Inventory / Warehouse | Violet #7B4FFF | Lilac #DCCBFF | Stock cards, bin maps |
| Shipments / Dispatch | Teal #00B8A9 | Aqua #B8F2ED | Tracking timelines |
| Alerts / Reorder | Coral Red #FF5A5F | Blush #FFD8D9 | Low-stock, overdue follow-ups |
| Neutral base | Charcoal #1E2230 / Off-white #F7F8FC | — | Backgrounds, text |

Dark-mode variant mirrors the same hues at reduced saturation on a #12141C base for factory/warehouse low-light use.

9.3 Animation & Motion Principles

- Status transitions animate physically: a lead card sliding from "New" → "Contacted" column uses a spring-eased slide+fade (Framer Motion type: spring, stiffness: 300, damping: 26), not an abrupt re-render.

- Live counters (today's leads, pending dispatches) count up/down with number-tween animation on change, not a static re-paint.

- WhatsApp send confirmation: a small paper-plane/check micro-animation on the message bubble on successful delivery, red pulse on failure.

- Stock level bars: animated fill bars (green→amber→red gradient tied to reorder threshold) that visibly deplete as orders reserve stock.

- Skeleton loaders, not blank spinners, for all data fetches — shimmering placeholder cards matching final layout shape.

- Toasts/notifications slide in from top-right with color-coded left border matching module color; auto-dismiss with a shrinking progress bar.

- Motion budget: keep transitions 150–300ms, respect prefers-reduced-motion for accessibility.

9.4 Key Screens (wireframe structure)

- Boss/Admin Dashboard — top KPI strip (animated counters: New Leads Today, Pending Follow-ups, Orders in Transit, Low Stock SKUs) → below, a 2x2 grid: Lead Funnel (animated horizontal funnel), Sales Trend (line chart, animated draw-on), Inventory Health (donut, color-graded), Team Leaderboard (animated bar race for conversions).

- Lead Pipeline (Kanban) — columns New → Contacted → Qualified → Quoted → Won/Lost, drag-and-drop cards with color-left-border by source (IndiaMART orange, Web blue, Manual gray, WhatsApp green), inline quick-actions (call, WhatsApp, note).

- Lead/Contact Detail — timeline of all activities + WhatsApp thread embedded inline + quotation history, with a persistent "Next Action" sticky card.

- Inventory Dashboard — warehouse selector tabs, SKU table with animated stock bars, bin-location visual map (simple grid heatmap by occupancy), reorder alert rail.

- Order/Shipment Tracker — horizontal animated stepper (Confirmed → Processing → Dispatched → Delivered) per order, matching the color system.

- Automation Builder — visual trigger→condition→action rule builder (drag blocks), template preview panel showing WhatsApp bubble mockup live as you type.

- Mobile (PWA/React Native) — bottom tab nav (Leads / Orders / Inventory / Chat / More), swipe-to-call/WhatsApp on lead cards, push notifications for assignment and low-stock alerts, fully responsive down to 360px width.

10. Automation Rule Library (starter set)

| # | Trigger | Condition | Action |
| --- | --- | --- | --- |
| 1 | Lead created | source = IndiaMART | Send WhatsApp "thanks for inquiry" template within 2 min |
| 2 | Lead created | any | Auto-assign round-robin within active sales team |
| 3 | Lead status = new | no activity in 24h | WhatsApp follow-up #1 + notify assignee |
| 4 | Lead status = contacted | no reply in 72h | WhatsApp follow-up #2 |
| 5 | Lead status = contacted | no reply in 7 days | WhatsApp follow-up #3 (final) + auto-tag "cold" |
| 6 | Quotation sent | no response in 3 days | Reminder WhatsApp + task for employee to call |
| 7 | Order status → confirmed | any | Reserve stock; notify warehouse team |
| 8 | Order status → dispatched | any | WhatsApp tracking link to customer automatically |
| 9 | Order status → delivered | any | WhatsApp feedback/NPS request after 24h delay |
| 10 | Stock quantity_on_hand < reorder_point | any | Admin dashboard alert + daily digest email/WhatsApp |
| 11 | Lead marked "lost" | reason = price | Add to 90-day win-back campaign list |
| 12 | Customer WhatsApp reply contains opt-out keyword | any | Set do_not_contact=true, stop all sequences (compliance) |
| 13 | Payment overdue (order payment_status=pending, >X days) | any | WhatsApp payment reminder + admin alert |
| 14 | New user created by Admin | any | WhatsApp OTP to new employee's phone for first login |

Rules stored as trigger_event + condition_json + action_type + template_id, editable via the Automation Builder UI — no code deploy needed to add/adjust a rule.

11. Reporting & KPIs

| KPI | Formula / Definition | Refresh |
| --- | --- | --- |
| Lead-to-Order Conversion Rate | Orders won / Total leads (by period, source, employee) | Real-time |
| Avg. First Response Time | Time from lead.captured_at → first LEAD_ACTIVITY | Real-time |
| Follow-up Sequence Completion Rate | % leads completing full sequence before response | Daily |
| Stock Aging | Days since last movement per batch, bucketed (0-30/31-60/61-90/90+) | Daily |
| Reorder Compliance | % of reorder alerts actioned within SLA (e.g. 48h) | Daily |
| Shipping Accuracy | Orders delivered without return/complaint / total delivered | Weekly |
| On-Time Dispatch Rate | Dispatches within SLA of order confirmation | Daily |
| WhatsApp Campaign Performance | Sent / Delivered / Read / Replied per template | Real-time |
| Sales by Employee/Territory | Order value grouped by assignee/region | Real-time |
| Win/Loss Reason Breakdown | Count of lost_reason categories | Weekly |

Dashboards should support date-range compare (this month vs last) and CSV export for board-level reporting.

12. Security, Compliance, Backups & Monitoring

- India data protection (DPDP Act, 2023): treat customer phone/email/company data as personal data — capture consent at lead source where feasible (IndiaMART/website already imply consent to be contacted for the inquiry), honor opt-out/erasure requests, maintain a data-processing log, and avoid retaining data beyond a defined business-need window (configurable retention policy per entity).

- Access security: bcrypt/argon2 password hashing, JWT short-lived access tokens + refresh tokens, optional WhatsApp-OTP 2FA for admin roles, IP-restriction option for admin panel if needed.

- Encryption: TLS 1.2+ everywhere in transit; at-rest encryption on the database volume and object storage (most managed India-region cloud providers offer this by default).

- Backups: automated daily full DB backup + continuous WAL/point-in-time recovery (Postgres), 30-day retention minimum, backups stored in a separate region/bucket from primary, monthly restore-drill to verify integrity.

- Audit logging: every create/update/delete/status-change/login/permission-change recorded in AUDIT_LOG (actor, action, entity, before/after diff, IP, timestamp) — immutable, admin-readable only.

- Monitoring/SLA: uptime monitoring (e.g. UptimeRobot/Better Stack), error tracking (Sentry), structured logs shipped to a log aggregator, internal SLA target suggestion: 99.5% uptime business hours, WhatsApp webhook processing < 5s, page load < 2s on 4G.

- Rate limiting & webhook signature verification on all inbound integration endpoints (IndiaMART, WhatsApp) to prevent spoofed payloads.

13. Technology Stack Recommendation

| Layer | Recommendation | Why |
| --- | --- | --- |
| Frontend (Web) | React + TypeScript, Tailwind CSS, Framer Motion, Recharts/Chart.js | Fast to build vibrant animated UI; huge ecosystem; matches the color/motion system above |
| Mobile | React Native (or PWA first, native later) | Code-sharing with web team, push notifications, offline-friendly for warehouse floor |
| Backend | Node.js (NestJS) or Python (FastAPI/Django) | Both pair well with async webhook-heavy integration work; NestJS if team prefers TS end-to-end |
| Database | PostgreSQL (primary), Redis (queues, caching, session) | Relational integrity for inventory/orders; JSONB for flexible raw-payload storage |
| Queue/Jobs | BullMQ (Node) or Celery (Python) on Redis | Automation engine, scheduled reorder checks, WhatsApp sequence timers |
| File/Object storage | S3-compatible (AWS S3 / Backblaze B2 / DigitalOcean Spaces) | Quotation PDFs, product images, attachments |
| WhatsApp | BSP (Interakt/WATI/Gupshup/AiSensy) initially → Meta Cloud API direct once volume justifies it | Faster launch, template management UI, cost predictability |
| Hosting | AWS ap-south-1 (Mumbai) or equivalent India-region cloud | Data locality/latency for India-based team and compliance comfort |
| CI/CD | GitHub Actions → Docker containers → managed hosting (ECS/Fly.io/Render) | Simple, low-ops for a small team |
| Search (optional, phase 2+) | PostgreSQL full-text initially; Meilisearch/Elasticsearch if catalog grows large | Avoid overhead until product catalog scale demands it |

API pattern: REST + JSON for the core CRM API (simplicity, easy 3rd-party integration); webhooks for inbound IndiaMART/WhatsApp events; consider GraphQL only if the frontend team later wants flexible nested queries across leads/orders/inventory — not needed at launch.

14. Testing Strategy

| Layer | Approach |
| --- | --- |
| Unit tests | Core business logic — stock reservation math, automation rule evaluation, lead de-dupe logic. Target 70%+ coverage on services. |
| Integration tests | API endpoints against a test DB; webhook payload handling (IndiaMART/WhatsApp) with recorded fixture payloads. |
| E2E tests | Playwright/Cypress covering: lead capture → quotation → order → dispatch happy path; RBAC boundary tests (employee cannot see others' leads, etc.). |
| Load testing | k6/Locust on webhook ingestion (simulate lead bursts) and dashboard queries at target concurrency (30–50 users). |
| UAT | Structured UAT script with the actual sales/warehouse team before each phase go-live — this is where a "vibrant but usable" UI gets validated by real users, not just design review. |
| Security testing | Basic OWASP Top 10 pass (auth, injection, access control) before go-live; annual re-check as it grows. |

15. Phased Implementation Plan

Total: ~20 weeks (5 months) to full feature set, structured as 2-week sprints, front-loading the highest-value modules (leads + WhatsApp + inventory basics) so the team gets value within 6–8 weeks.

| Phase | Sprints | Weeks | Scope |
| --- | --- | --- | --- |
| Phase 0 — Foundation | Sprint 0 | Wk 1–2 | Requirements sign-off, data model finalization, environment setup, auth/RBAC skeleton, design system build (colors/components/animation tokens), CI/CD pipeline |
| Phase 1 — Lead Core | Sprint 1–2 | Wk 3–6 | Lead CRUD, IndiaMART integration, manual entry, CSV import, lead Kanban UI, contact/company model, basic dashboard |
| Phase 2 — WhatsApp Automation | Sprint 3–4 | Wk 7–10 | BSP integration, template library, automation rule engine (v1: triggers 1–6, 12 from Section 10), inbound message sync, sequence scheduler |
| Phase 3 — Orders & Inventory | Sprint 5–7 | Wk 11–16 | Quotation builder, order lifecycle, product/SKU catalog, warehouse/bin model, stock movements, reorder alerts, batch tracking, shipment tracking + dispatch notifications |
| Phase 4 — Reporting & Polish | Sprint 8–9 | Wk 17–19 | Full KPI dashboards, exportable reports, animation polish pass, mobile app/PWA hardening, audit log UI, performance tuning |
| Phase 5 — UAT, Hardening, Go-Live | Sprint 10 | Wk 20 | Security pass, load testing, backup/DR drill, user training, phased rollout (pilot team → full team) |

Post-launch (Phase 6, ongoing): telephony/VoIP integration, advanced sales forecasting, win-back campaign automation, multi-warehouse transfer optimization, native mobile app (if PWA proves insufficient).

16. Resource & Cost Estimates (India-based delivery)

16.1 Team Composition (for the 20-week build)

| Role | Allocation | Notes |
| --- | --- | --- |
| Tech Lead / Architect | Full-time | Owns architecture, code review, integration design |
| Backend Developer x2 | Full-time | API, automation engine, integrations, inventory logic |
| Frontend Developer x2 | Full-time | React web app, animation system, dashboards |
| Mobile/PWA Developer | Full-time from Phase 3 | Mobile responsiveness & app |
| UI/UX Designer | Full-time Phase 0–1, part-time after | Design system, wireframes, animation spec |
| QA Engineer | Part-time ramping to full-time Phase 4–5 | Test plans, E2E automation |
| DevOps (part-time/shared) | ~0.25 FTE throughout | CI/CD, hosting, monitoring, backups |
| Project Manager | Part-time | Sprint planning, client coordination |

16.2 Indicative Cost Bands (India market rates, INR — broad ranges since rates vary by city/seniority)

| Item | Low estimate | High estimate |
| --- | --- | --- |
| Development team (20 weeks, blended team above) | ₹22,00,000 | ₹45,00,000 |
| UI/UX design system & wireframes | ₹2,00,000 | ₹5,00,000 |
| WhatsApp BSP subscription (ongoing, monthly) | ₹3,000–8,000/mo | ₹15,000–40,000/mo (volume-dependent) |
| Meta WhatsApp conversation charges | Pay-per-conversation, India rates ~₹0.35–₹0.90/conversation category-dependent | — |
| Cloud hosting (DB + app + storage, India region) | ₹8,000/mo | ₹35,000/mo (scales with usage) |
| IndiaMART API access | Usually bundled with your IndiaMART paid plan | Confirm with account manager |
| Domain/SSL/misc SaaS (Sentry, monitoring, email) | ₹3,000/mo | ₹10,000/mo |
| QA/security testing pass | ₹1,50,000 | ₹4,00,000 |
| Total build (one-time) | ~₹25–30 lakh | ~₹55–60 lakh |
| Ongoing run cost (monthly, post-launch) | ~₹15,000–20,000 | ~₹90,000–1,10,000 |

These are directional planning ranges for budgeting conversations, not vendor quotes — actual numbers depend heavily on whether you build with an in-house team, a dev agency, or a hybrid, and on final integration/message volumes. I'd treat this as a starting point to RFQ against, not a fixed budget.

16.3 Cost-saving levers if budget is tighter

- Start with Phase 0–2 only (Foundation + Leads + WhatsApp) as an MVP — this alone typically delivers the biggest ROI (faster response times, no lost IndiaMART leads) for roughly 40% of total budget.

- Use a low-code inventory module initially (even a well-structured Airtable/NocoDB layer behind the same API contract) and migrate to custom-built inventory in Phase 3 once cash flow allows.

- Defer native mobile app; PWA covers most "on-the-go" needs at a fraction of the cost.

17. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Meta/WhatsApp template rejection delays launch | Submit templates for approval in Sprint 0, not Sprint 3; keep a fallback of manual WhatsApp send for first 2 weeks |
| IndiaMART API rate limits / plan restrictions | Confirm API tier with IndiaMART account manager before Sprint 1; build pull-based fallback with backoff |
| Inventory data migration from spreadsheets is messy | Dedicate explicit CSV-cleanup sprint time in Phase 3; validate with a warehouse staff walkthrough before cutover |
| Team resists new system vs. familiar WhatsApp+Excel habits | Pilot with 1–2 employees first (Phase 5), gather feedback, make automation visibly reduce their manual work early |
| Scope creep on "fully animated" UI delaying core function delivery | Design system tokens locked in Phase 0; animation applied to existing components incrementally, never blocking a functional release |

Next Steps

- Confirm/adjust the assumptions in the header (team size, warehouse count, budget band, WhatsApp BSP preference).

- Confirm IndiaMART API tier and current WhatsApp Business API status (do you already have a Meta Business verification in progress?).

- Approve the phased plan and starting team composition, or scope down to an MVP (Phase 0–2) per Section 16.3.

- I can turn any single section — ER diagram, sprint backlog, RBAC matrix, or the automation rule set — into its own working spreadsheet/Word doc/board-ready deck if that's more useful for stakeholder review.